# Campus Marketplace (NJIT) — Agile Planning Package

Themes • Epics • Use Cases • Backlog • Sprint Plan • Traceability

Version v8 — 2026-02-20

Purpose: This document is ONLY for Agile planning. Technical architecture and implementation details live in separate project docs.

# Table of Contents

Ctrl+Click entries to jump (Word).

1) Product & MVP Scope

2) Themes

3) Epics

4) Use Cases (Core MVP)

UC1 — Sign up / Log in with NJIT email

UC2 — Create/Edit Profile (Student or Business)

UC3 — Post Listing (Item or Service)

UC4 — Browse/Search Listings

UC5 — Message Seller / Booking Lite

5) User Stories Backlog

5.1 Backlog Overview (Compact)

6) Sprint Plan (5 Sprints)

S1 — Manage & Define (Feb 12 – Feb 24)

S2 — Design (Feb 26 – Mar 5)

S3 — Backend Foundations (Mar 10 – Mar 19)

S4 — Core Features Development (Mar 24 – Apr 3)

S5 — MVP Completion, QA & Showcase Prep (Apr 7 – Apr 30 (final presentations May 3; paper May 7))

7) Traceability Matrix

8) Risks & Mitigations

Appendix A) Full User Story Details

E1 — Authentication & Session Management

E2 — Authorization, RLS & Data Protection Baseline

E3 — Profiles (Student + Business)

E4 — Listing Data Model + Media

E5 — Create & Manage Listings (Items + Services)

E6 — Browse, Detail & Search

E7 — Messaging (Conversations + Messages)

E8 — Booking Lite (Optional, built on messaging)

E9 — DevOps, Repo Standards & CI/CD

E10 — Testing, QA & Demo Scripts

# 1) Product & MVP Scope

MVP user value: NJIT students can safely post and discover items/services and coordinate via basic messaging or booking.

MVP includes:

NJIT-only email verification for access

Student profiles + student business profiles

Item + service listings (post, browse, simple search)

Basic messaging OR booking (lite)

Clean, modern UI

Out of scope (unless the team explicitly adds later):

Payments

Ratings/reviews

Advanced search filters

Push notifications

Multi-campus expansion

Platform constraints:

Supabase for Auth + Postgres + Storage + RLS

5-sprint class timeline (Feb → May)

# 2) Themes

| Theme | Goal | Success Metrics |
| --- | --- | --- |
| T1 — Campus-Verified Access & Safety | Create a marketplace that is trusted because only NJIT users can join and all data access is correctly protected. | 100% of active users are verified via @njit.edu email verification. RLS policies prevent unauthorized reads/writes in basic security tests. No unauthenticated access to protected pages or APIs. |
| T2 — Profiles & Trust Signals | Give students and student-run businesses clear, useful profiles so buyers can judge legitimacy and contact the right person. | Users can create and edit a profile in under 2 minutes. At least 80% of test users complete required profile fields. Business profiles are clearly distinguishable from standard profiles. |
| T3 — Listings & Discovery | Enable posting and discovery of items/services with a simple, fast browsing and search experience. | A user can post an item/service listing end-to-end (including an image) successfully. Browse page loads listings with pagination and shows usable empty states. Keyword search + type filter returns expected results in test cases. |
| T4 — Messaging & Booking Lite | Let buyers and sellers coordinate through basic in-app messaging (and optional lightweight booking requests) without payments. | Users can message from a listing and see the conversation in an inbox. Only conversation participants can view messages (RLS enforced). Booking requests can be accepted/declined if enabled. |
| T5 — Quality Delivery & Demo Readiness | Ship working increments every sprint with clear definition of done, CI checks, and documentation aligned to capstone deliverables. | CI runs on PRs (lint + typecheck + build) and blocks broken merges. Every demo includes an end-to-end vertical slice. Setup/documentation enables new team member onboarding in <30 minutes. |

# 3) Epics

| Epic | Theme | Objective | Primary Owner |
| --- | --- | --- | --- |
| E1 — Authentication & Session Management | T1 | Implement Supabase Auth with NJIT email restrictions, email verification, and guarded routes. | Backend Lead + Frontend |
| E2 — Authorization, RLS & Data Protection Baseline | T1 | Define and enforce RLS policies and storage rules so only authorized users can read/write sensitive data. | Backend Lead + Backend Support |
| E3 — Profiles (Student + Business) | T2 | Create profile pages and APIs for students and student-run businesses, including avatar support. | Frontend + Backend Support + UX |
| E4 — Listing Data Model + Media | T3 | Design listing schema that supports items and services and store listing images in Supabase Storage. | Backend Lead + Backend Support |
| E5 — Create & Manage Listings (Items + Services) | T3 | Implement create/edit/publish/unpublish and soft-delete flows for listings. | Frontend + Backend |
| E6 — Browse, Detail & Search | T3 | Implement browse feed, listing detail, and simple search by keyword and type. | Frontend |
| E7 — Messaging (Conversations + Messages) | T4 | Allow users to start a conversation from a listing and exchange messages; implement inbox and thread views. | Backend Support + Frontend |
| E8 — Booking Lite (Optional, built on messaging) | T4 | Add optional booking request fields and statuses inside conversations. | PM + UX + Backend Support + Frontend |
| E9 — DevOps, Repo Standards & CI/CD | T5 | Set up monorepo structure, linting, formatting, and CI pipeline; enable Vercel deployments. | Backend Support + Frontend + PM |
| E10 — Testing, QA & Demo Scripts | T5 | Define DoD, write smoke tests, run usability tests, and prepare midterm/final demos. | PM + UX + All Devs |

# 4) Use Cases (Core MVP)

Use cases below define the end-to-end flows that each sprint should keep demoable.

## UC1 — Sign up / Log in with NJIT email

Actor(s): Student

Preconditions: Account verified (email)

Main flow:

Create account

Verify email

Login

Access app

Failure/alternate flows:

Non-NJIT email rejected

Unverified email blocked

## UC2 — Create/Edit Profile (Student or Business)

Actor(s): Authenticated user

Preconditions: Logged in

Main flow:

Create profile

Mark business (optional)

Save

View profile

Failure/alternate flows:

Validation errors

RLS denial

## UC3 — Post Listing (Item or Service)

Actor(s): Seller

Preconditions: Profile exists

Main flow:

Create draft listing

Upload image

Publish

Failure/alternate flows:

Upload fails → retry

Missing required fields → block publish

## UC4 — Browse/Search Listings

Actor(s): Buyer

Preconditions: Listings published

Main flow:

Browse feed

Filter type

Search keyword

Open listing detail

Failure/alternate flows:

Empty state

Network error → retry

## UC5 — Message Seller / Booking Lite

Actor(s): Buyer + Seller

Preconditions: Viewing listing; both logged in

Main flow:

Start conversation

Send message

Reply

Failure/alternate flows:

Self-message blocked

Non-participant access denied

# 5) User Stories Backlog

Backlog is split into a compact planning view and a full story details appendix.

## 5.1 Backlog Overview (Compact)

| Story ID | Epic | Title | Priority | Points | Primary Owner | Sprint |
| --- | --- | --- | --- | --- | --- | --- |
| CM-US-001 | E9 | Monorepo initialization + conventions | Must | 3 | Backend Support + Frontend | S1 |
| CM-US-002 | E9 | CI pipeline baseline (lint/type/build) | Must | 3 | Backend Support | S1 |
| CM-US-003 | E10 | Definition of Done + PR checklist | Must | 2 | PM | S1 |
| CM-US-004 | E10 | User research plan + survey draft | Must | 3 | PM + UX | S1 |
| CM-US-005 | E4 | Draft core data model (ERD + table list) | Must | 5 | Backend Lead + Backend Support | S1 |
| CM-US-006 | E10 | Low-fidelity wireframes for core flows | Must | 3 | UX | S2 |
| CM-US-007 | E10 | Branding + design tokens v1 | Should | 3 | UX + Frontend | S2 |
| CM-US-008 | E6 | Static page scaffold (routes + layout) | Must | 5 | Frontend | S2 |
| CM-US-009 | E4 | Finalize schema requirements from wireframes | Must | 3 | Backend Lead | S2 |
| CM-US-010 | E1 | Sign-up UI with NJIT domain validation | Must | 3 | Frontend | S3 |
| CM-US-011 | E1 | Supabase Auth domain restriction + email verification | Must | 5 | Backend Lead | S3 |
| CM-US-012 | E1 | Login/Logout + session persistence | Must | 3 | Frontend | S3 |
| CM-US-013 | E2 | Create core tables + migrations (profiles, listings, images, conversa… | Must | 8 | Backend Lead + Backend Support | S3 |
| CM-US-014 | E2 | RLS policies for profiles and listings | Must | 5 | Backend Lead | S3 |
| CM-US-015 | E2 | RLS policies for conversations and messages | Must | 5 | Backend Support | S3 |
| CM-US-016 | E3 | Profile create/edit (baseline fields) | Must | 5 | Frontend | S3 |
| CM-US-017 | E3 | Business profile toggle + business fields | Should | 3 | Frontend + UX | S3 |
| CM-US-018 | E9 | Environment variables + secrets strategy | Must | 2 | Backend Support + PM | S3 |
| CM-US-019 | E4 | Supabase Storage bucket for listing images | Must | 5 | Backend Lead + Frontend | S4 |
| CM-US-020 | E5 | Create item listing (draft) from form | Must | 5 | Frontend | S4 |
| CM-US-021 | E5 | Create service listing (draft) from form | Must | 5 | Frontend + UX | S4 |
| CM-US-022 | E5 | Publish/unpublish listing | Must | 3 | Frontend + Backend Support | S4 |
| CM-US-023 | E6 | Browse feed (published listings only) + pagination | Must | 5 | Frontend | S4 |
| CM-US-024 | E6 | Listing detail page | Must | 3 | Frontend | S4 |
| CM-US-025 | E6 | Simple search (keyword + type filter) | Should | 3 | Frontend + Backend Support | S4 |
| CM-US-026 | E10 | Midterm demo script + walkthrough deck (lightweight) | Must | 3 | PM | S4 |
| CM-US-027 | E7 | Create or get conversation from listing | Must | 5 | Backend Support + Frontend | S5 |
| CM-US-028 | E7 | Inbox view (list conversations with previews) | Must | 5 | Frontend | S5 |
| CM-US-029 | E7 | Message thread + send message | Must | 8 | Frontend + Backend Support | S5 |
| CM-US-030 | E7 | Realtime updates (or polling fallback) for messages | Should | 5 | Frontend | S5 |
| CM-US-031 | E8 | Booking request message type (optional) | Could | 5 | Frontend + Backend Support + UX | S5 |
| CM-US-032 | E9 | Production deployment (Vercel + Supabase) with environments | Must | 5 | Backend Lead + Frontend | S5 |
| CM-US-033 | E10 | E2E smoke tests for core flows | Should | 5 | Backend Support + Frontend | S5 |
| CM-US-034 | E10 | Final usability test + polish backlog | Must | 3 | UX + Frontend + PM | S5 |
| CM-US-035 | E10 | Final presentation narrative + paper outline | Must | 3 | PM | S5 |
| CM-US-036 | E10 | Marketplace rules & restricted content policy (MVP) | Should | 2 | PM | S2 |
| CM-US-037 | E9 | Project board workflow (columns + labels + templates) | Must | 2 | PM | S2 |
| CM-US-038 | E9 | API contract + data dictionary doc | Must | 3 | Backend Lead + Frontend | S2 |
| CM-US-039 | E9 | Supabase client wrapper + service layer scaffold | Must | 5 | Frontend | S3 |
| CM-US-040 | E10 | Error handling patterns (loading, empty, failure states) | Must | 3 | Frontend + UX | S3 |
| CM-US-041 | E1 | Password reset flow | Should | 3 | Frontend | S3 |
| CM-US-042 | E3 | Public profile view (read-only) | Must | 3 | Frontend | S4 |
| CM-US-043 | E3 | Avatar upload (profile picture) | Could | 3 | Frontend + Backend Support | S4 |
| CM-US-044 | E5 | My Listings dashboard | Must | 5 | Frontend | S4 |
| CM-US-045 | E5 | Edit listing (item/service) | Must | 5 | Frontend + Backend Support | S4 |
| CM-US-046 | E5 | Soft delete listing | Must | 3 | Backend Support + Frontend | S4 |
| CM-US-047 | E7 | Messaging schema + RLS validation smoke checks | Must | 5 | Backend Support | S4 |
| CM-US-048 | E1 | Account deactivation (soft delete) UX | Could | 5 | Backend Lead + Frontend | S5 |
| CM-US-049 | E6 | Performance baseline: indexes + query limits | Should | 3 | Backend Lead | S5 |
| CM-US-050 | E10 | Demo seed data + demo accounts (staging) | Should | 3 | Backend Support + PM | S5 |

# 6) Sprint Plan (5 Sprints)

## S1 — Manage & Define (Feb 12 – Feb 24)

Sprint goal: Vision, MVP scope, tools, repo + CI skeleton, initial schema and research plan.

| Story ID | Title | Pts | Owner |
| --- | --- | --- | --- |
| CM-US-001 | Monorepo initialization + conventions | 3 | Backend Support + Frontend |
| CM-US-002 | CI pipeline baseline (lint/type/build) | 3 | Backend Support |
| CM-US-003 | Definition of Done + PR checklist | 2 | PM |
| CM-US-004 | User research plan + survey draft | 3 | PM + UX |
| CM-US-005 | Draft core data model (ERD + table list) | 5 | Backend Lead + Backend Support |

Definition of Done:

Acceptance criteria met

Basic error handling and empty/loading states

Integrated to dev branch

RLS/permissions correct where applicable

Demoable end-to-end slice

## S2 — Design (Feb 26 – Mar 5)

Sprint goal: User flows + wireframes + branding; static UI scaffold; finalize schema details and Supabase setup.

| Story ID | Title | Pts | Owner |
| --- | --- | --- | --- |
| CM-US-006 | Low-fidelity wireframes for core flows | 3 | UX |
| CM-US-007 | Branding + design tokens v1 | 3 | UX + Frontend |
| CM-US-008 | Static page scaffold (routes + layout) | 5 | Frontend |
| CM-US-009 | Finalize schema requirements from wireframes | 3 | Backend Lead |
| CM-US-036 | Marketplace rules & restricted content policy (MVP) | 2 | PM |
| CM-US-037 | Project board workflow (columns + labels + templates) | 2 | PM |
| CM-US-038 | API contract + data dictionary doc | 3 | Backend Lead + Frontend |

Definition of Done:

Acceptance criteria met

Basic error handling and empty/loading states

Integrated to dev branch

RLS/permissions correct where applicable

Demoable end-to-end slice

## S3 — Backend Foundations (Mar 10 – Mar 19)

Sprint goal: Auth + core DB schema with RLS; frontend auth integration; profile basics.

| Story ID | Title | Pts | Owner |
| --- | --- | --- | --- |
| CM-US-010 | Sign-up UI with NJIT domain validation | 3 | Frontend |
| CM-US-011 | Supabase Auth domain restriction + email verification | 5 | Backend Lead |
| CM-US-012 | Login/Logout + session persistence | 3 | Frontend |
| CM-US-013 | Create core tables + migrations (profiles, listings, images, conversa… | 8 | Backend Lead + Backend Support |
| CM-US-014 | RLS policies for profiles and listings | 5 | Backend Lead |
| CM-US-015 | RLS policies for conversations and messages | 5 | Backend Support |
| CM-US-016 | Profile create/edit (baseline fields) | 5 | Frontend |
| CM-US-017 | Business profile toggle + business fields | 3 | Frontend + UX |
| CM-US-018 | Environment variables + secrets strategy | 2 | Backend Support + PM |
| CM-US-039 | Supabase client wrapper + service layer scaffold | 5 | Frontend |
| CM-US-040 | Error handling patterns (loading, empty, failure states) | 3 | Frontend + UX |
| CM-US-041 | Password reset flow | 3 | Frontend |

Definition of Done:

Acceptance criteria met

Basic error handling and empty/loading states

Integrated to dev branch

RLS/permissions correct where applicable

Demoable end-to-end slice

## S4 — Core Features Development (Mar 24 – Apr 3)

Sprint goal: Listings (post/browse/search) + initial messaging/booking; midterm demo readiness.

| Story ID | Title | Pts | Owner |
| --- | --- | --- | --- |
| CM-US-019 | Supabase Storage bucket for listing images | 5 | Backend Lead + Frontend |
| CM-US-020 | Create item listing (draft) from form | 5 | Frontend |
| CM-US-021 | Create service listing (draft) from form | 5 | Frontend + UX |
| CM-US-022 | Publish/unpublish listing | 3 | Frontend + Backend Support |
| CM-US-023 | Browse feed (published listings only) + pagination | 5 | Frontend |
| CM-US-024 | Listing detail page | 3 | Frontend |
| CM-US-025 | Simple search (keyword + type filter) | 3 | Frontend + Backend Support |
| CM-US-026 | Midterm demo script + walkthrough deck (lightweight) | 3 | PM |
| CM-US-042 | Public profile view (read-only) | 3 | Frontend |
| CM-US-043 | Avatar upload (profile picture) | 3 | Frontend + Backend Support |
| CM-US-044 | My Listings dashboard | 5 | Frontend |
| CM-US-045 | Edit listing (item/service) | 5 | Frontend + Backend Support |
| CM-US-046 | Soft delete listing | 3 | Backend Support + Frontend |
| CM-US-047 | Messaging schema + RLS validation smoke checks | 5 | Backend Support |

Definition of Done:

Acceptance criteria met

Basic error handling and empty/loading states

Integrated to dev branch

RLS/permissions correct where applicable

Demoable end-to-end slice

## S5 — MVP Completion, QA & Showcase Prep (Apr 7 – Apr 30 (final presentations May 3; paper May 7))

Sprint goal: Finish messaging, polish UI, deploy, test, document, and prepare final showcase.

| Story ID | Title | Pts | Owner |
| --- | --- | --- | --- |
| CM-US-027 | Create or get conversation from listing | 5 | Backend Support + Frontend |
| CM-US-028 | Inbox view (list conversations with previews) | 5 | Frontend |
| CM-US-029 | Message thread + send message | 8 | Frontend + Backend Support |
| CM-US-030 | Realtime updates (or polling fallback) for messages | 5 | Frontend |
| CM-US-031 | Booking request message type (optional) | 5 | Frontend + Backend Support + UX |
| CM-US-032 | Production deployment (Vercel + Supabase) with environments | 5 | Backend Lead + Frontend |
| CM-US-033 | E2E smoke tests for core flows | 5 | Backend Support + Frontend |
| CM-US-034 | Final usability test + polish backlog | 3 | UX + Frontend + PM |
| CM-US-035 | Final presentation narrative + paper outline | 3 | PM |
| CM-US-048 | Account deactivation (soft delete) UX | 5 | Backend Lead + Frontend |
| CM-US-049 | Performance baseline: indexes + query limits | 3 | Backend Lead |
| CM-US-050 | Demo seed data + demo accounts (staging) | 3 | Backend Support + PM |

Definition of Done:

Acceptance criteria met

Basic error handling and empty/loading states

Integrated to dev branch

RLS/permissions correct where applicable

Demoable end-to-end slice

# 7) Traceability Matrix

| Requirement | Theme | Epic(s) | Story IDs | Sprint(s) |
| --- | --- | --- | --- | --- |
| NJIT-only .edu verification | T1 | E1,E2 | CM-US-010, CM-US-011, CM-US-012 | S3 |
| User profiles + business profiles | T2 | E3 | CM-US-016, CM-US-017, CM-US-039 | S3–S4 |
| Item + service listings (post/browse/search) | T3 | E4,E5,E6 | CM-US-019, CM-US-020–CM-US-025, CM-US-041–CM-US-043 | S4–S5 |
| Basic messaging / booking | T4 | E7,E8 | CM-US-044, CM-US-027–CM-US-031 | S4–S5 |
| CI/CD + DoD + testing | T5 | E9,E10 | CM-US-001–CM-US-003, CM-US-033 | S1–S5 |

# 8) Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Auth domain restriction complexity | Blocks MVP access | Start early in Sprint 3; keep fallback plan for temporary manual gate only if needed. |
| RLS misconfiguration | Security + broken UX | Peer review policies; test with two users; RLS smoke checks. |
| Messaging realtime complexity | Schedule risk | Polling fallback; treat realtime as Should, not Must. |
| Scope creep (payments/reviews/advanced filters) | Delays MVP | Keep out-of-scope list; PM enforces MoSCoW. |
| Deployment issues near final demo | Demo instability | Deploy early; keep rollback; use seed data; run smoke tests. |

# Appendix A) Full User Story Details

## E1 — Authentication & Session Management

### CM-US-003 — Definition of Done + PR checklist

As a PM, I want a Definition of Done and PR checklist so that every increment is demo-ready and testable.

Priority: Must | Points: 2 | Owner: PM | Sprint: S1

Dependencies: CM-US-001

Security/Data Notes: DoD includes RLS considerations for any data access change.

Acceptance Criteria:

Given a story is moved to Done, when we verify the DoD checklist, then acceptance criteria are met and basic error handling exists.

Given a PR is submitted, when reviewer checks the PR template, then tests/lint/build and screenshots (if UI) are included.

Given new endpoints/contracts, when merged, then docs are updated (API contract or README).

### CM-US-004 — User research plan + survey draft

As a PM, I want a lightweight research plan and survey so that we validate the MVP flows with real NJIT students early.

Priority: Must | Points: 3 | Owner: PM + UX | Sprint: S1

Dependencies: None

Security/Data Notes: No PII stored in repo; responses stored in shared doc drive.

Acceptance Criteria:

Given a draft survey, when reviewed by the team, then it covers buying, selling, services, and trust concerns.

Given we run the survey, when sprint ends, then we have a target list of at least 10 participants and a plan to recruit them.

Given results arrive, when summarized, then top 5 insights are documented with recommended UX changes.

### CM-US-006 — Low-fidelity wireframes for core flows

As a user, I want to see simple wireframes so that I understand how the app will work before development.

Priority: Must | Points: 3 | Owner: UX | Sprint: S2

Dependencies: CM-US-004

Security/Data Notes: No security notes; but include trust messaging (NJIT-only).

Acceptance Criteria:

Given core flows, when wireframes are created, then they cover auth, browse, listing detail, post listing, profile, messages.

Given a review session, when we walkthrough wireframes, then feedback is captured and prioritized.

Given wireframes are approved, when sprint ends, then they are shared in Figma and linked from the project board.

### CM-US-007 — Branding + design tokens v1

As a developer, I want basic design tokens so that the UI is consistent and fast to implement.

Priority: Should | Points: 3 | Owner: UX + Frontend | Sprint: S2

Dependencies: CM-US-006

Security/Data Notes: Avoid exposing sensitive info; consider accessible contrast ratios.

Acceptance Criteria:

Given branding assets, when delivered, then logo, color palette, and typography are documented.

Given tokens, when implemented, then primary/secondary colors and type scale are available in Tailwind config or CSS variables.

Given components, when built, then they reuse tokens and avoid one-off styling.

### CM-US-010 — Sign-up UI with NJIT domain validation

As a prospective user, I want the sign-up form to accept only NJIT emails so that the platform stays campus-verified.

Priority: Must | Points: 3 | Owner: Frontend | Sprint: S3

Dependencies: CM-US-008

Security/Data Notes: Client-side validation is not sufficient; backend enforcement in CM-US-011.

Acceptance Criteria:

Given I enter an email not ending with @njit.edu, when I submit, then I see an error explaining NJIT-only access.

Given I enter a valid NJIT email and strong password, when I submit, then I see a confirmation message and verification instructions.

Given the backend rejects a domain, when the error returns, then the UI shows a safe, user-friendly message.

### CM-US-011 — Supabase Auth domain restriction + email verification

As the platform, I want domain restriction and email verification enforced so that only verified NJIT users can access protected features.

Priority: Must | Points: 5 | Owner: Backend Lead | Sprint: S3

Dependencies: CM-US-002

Security/Data Notes: Use Supabase Auth config or edge function; verify email_confirmed; block unverified in app logic + RLS.

Acceptance Criteria:

Given a sign-up attempt with a non-NJIT email, when Supabase receives it, then the account is not created (or is immediately blocked).

Given a new NJIT account, when the user has not verified email, then protected pages and data calls are denied.

Given a verified user, when they log in, then they can access protected routes and API calls.

### CM-US-012 — Login/Logout + session persistence

As a user, I want to log in and stay logged in so that I don’t need to re-authenticate constantly.

Priority: Must | Points: 3 | Owner: Frontend | Sprint: S3

Dependencies: CM-US-010, CM-US-011

Security/Data Notes: Use Supabase client auth listener; do not store service role keys client-side.

Acceptance Criteria:

Given a verified account, when I log in, then I am redirected to Browse and session is stored securely.

Given I refresh the page, when the app loads, then it restores the session and keeps me logged in.

Given I click logout, when confirmed, then my session is cleared and I return to the landing/login screen.

### CM-US-026 — Midterm demo script + walkthrough deck (lightweight)

As a team, we want a midterm demo script so that we can present a coherent end-to-end MVP slice.

Priority: Must | Points: 3 | Owner: PM | Sprint: S4

Dependencies: CM-US-023, CM-US-024

Security/Data Notes: Avoid promising payments/reviews; highlight NJIT-only trust and Supabase security.

Acceptance Criteria:

Given completed features, when we rehearse, then demo covers auth → profile → post listing → browse → view listing.

Given the deck, when reviewed, then it matches current product and includes risks/next steps.

Given submission requirements, when we submit, then midterm deliverables are complete by Apr 3.

### CM-US-033 — E2E smoke tests for core flows

As a team, we want automated smoke tests so that we catch obvious breakage before demos.

Priority: Should | Points: 5 | Owner: Backend Support + Frontend | Sprint: S5

Dependencies: CM-US-032

Security/Data Notes: Use Playwright as suggested; ensure test accounts and cleanup; don’t expose secrets in logs.

Acceptance Criteria:

Given CI runs, when smoke tests execute, then sign in → create listing → browse → open detail passes on staging.

Given messaging is enabled, when test runs, then create conversation and send a message passes.

Given tests fail, when failure occurs, then logs/screenshots are captured for debugging.

### CM-US-034 — Final usability test + polish backlog

As a UX/UI designer, I want a final usability pass so that the UI is clean and demo-ready.

Priority: Must | Points: 3 | Owner: UX + Frontend + PM | Sprint: S5

Dependencies: CM-US-032

Security/Data Notes: Avoid scope creep; prioritize blockers to demo; keep accessibility in mind.

Acceptance Criteria:

Given MVP is integrated, when we test with 5+ students, then top issues are captured with severity labels.

Given critical issues, when fixed, then we verify improvements with at least one re-test.

Given UI polish changes, when merged, then they do not break core flows and meet DoD.

### CM-US-035 — Final presentation narrative + paper outline

As a PM, I want a coherent final narrative so that the team can present and write the final paper efficiently.

Priority: Must | Points: 3 | Owner: PM | Sprint: S5

Dependencies: CM-US-032

Security/Data Notes: Do not claim out-of-scope features; emphasize Supabase RLS and NJIT-only trust.

Acceptance Criteria:

Given the project state, when we draft the deck, then it includes problem, solution, demo, architecture, and future scope (payments/reviews).

Given deadlines, when we prepare, then final presentation is ready by May 3 and paper outline by May 7.

Given the deck, when rehearsed, then every team member has a speaking role and a backup plan for demo failures.

### CM-US-036 — Marketplace rules & restricted content policy (MVP)

As a PM, I want clear marketplace rules (allowed items/services) so that the app stays safe and within school expectations.

Priority: Should | Points: 2 | Owner: PM | Sprint: S2

Dependencies: CM-US-004

Security/Data Notes: Policy only; no automated moderation in MVP; store in docs and link in UI.

Acceptance Criteria:

Given the MVP scope, when rules are written, then they define prohibited items/services and basic enforcement approach (manual for MVP).

Given the rules, when users view Post, then they can access the rules link before posting.

Given a report from user research, when risks are found, then rules are updated and shared with the team.

### CM-US-040 — Error handling patterns (loading, empty, failure states)

As a user, I want clear loading and error states so that the app feels reliable.

Priority: Must | Points: 3 | Owner: Frontend + UX | Sprint: S3

Dependencies: CM-US-008

Security/Data Notes: Avoid leaking raw errors; map Supabase errors to safe messages.

Acceptance Criteria:

Given a data request, when loading, then a skeleton/spinner shows and buttons are disabled appropriately.

Given a network error, when it happens, then user sees a friendly message and a Retry action.

Given no data, when empty, then a helpful empty state is displayed (not a blank page).

### CM-US-041 — Password reset flow

As a user, I want to reset my password so that I can regain access if I forget it.

Priority: Should | Points: 3 | Owner: Frontend | Sprint: S3

Dependencies: CM-US-012

Security/Data Notes: Use Supabase password reset; do not reveal whether an email is registered.

Acceptance Criteria:

Given I enter my NJIT email, when I request reset, then I receive a password reset email via Supabase.

Given I open the reset link, when I set a new password, then I can log in with the new password.

Given invalid/expired links, when used, then the app shows an error and allows requesting a new reset link.

### CM-US-048 — Account deactivation (soft delete) UX

As a user, I want to deactivate my account so that I can leave the platform without exposing my data.

Priority: Could | Points: 5 | Owner: Backend Lead + Frontend | Sprint: S5

Dependencies: CM-US-032, CM-US-014

Security/Data Notes: Prefer soft delete; ensure RLS prevents access; handle orphaned listings/messages carefully.

Acceptance Criteria:

Given I am logged in, when I request deactivation, then I must confirm and understand consequences.

Given my account is deactivated, when I try to log in, then access is blocked and I see a support message.

Given my account is deactivated, when others view my listings/profile, then they are hidden or show unavailable.

## E2 — Authorization, RLS & Data Protection Baseline

### CM-US-013 — Create core tables + migrations (profiles, listings, images, conversations, messages)

As a backend developer, I want the MVP tables created via migrations so that schema is versioned and reproducible.

Priority: Must | Points: 8 | Owner: Backend Lead + Backend Support | Sprint: S3

Dependencies: CM-US-005, CM-US-009

Security/Data Notes: Use Supabase migrations; avoid breaking changes without migration; include indexes for search fields.

Acceptance Criteria:

Given migrations run, when applied to a fresh database, then all MVP tables exist with primary/foreign keys.

Given item/service listings, when stored, then they share a common listings table with a type field and optional subfields as needed.

Given audit needs, when tables are created, then created_at and updated_at exist (and deleted_at if soft delete chosen).

### CM-US-014 — RLS policies for profiles and listings

As the platform, I want RLS policies so users can only edit their own profile and listings.

Priority: Must | Points: 5 | Owner: Backend Lead | Sprint: S3

Dependencies: CM-US-013

Security/Data Notes: RLS per proposal: profiles owner-only write; listings owner-only write; allow read of published, non-deleted listings.

Acceptance Criteria:

Given I am authenticated, when I select profiles, then I can read profiles (per MVP) but only update my own.

Given I try to update another user’s profile or listing, when the update is attempted, then it is denied by RLS.

Given I create a listing, when inserted, then owner_id is set to auth.uid() and cannot be spoofed.

### CM-US-050 — Demo seed data + demo accounts (staging)

As a team, we want stable demo data so that demos are consistent and fast.

Priority: Should | Points: 3 | Owner: Backend Support + PM | Sprint: S5

Dependencies: CM-US-032

Security/Data Notes: Seed only in staging; never seed production with fake users unless allowed; avoid PII.

Acceptance Criteria:

Given staging environment, when we run a seed script, then it creates sample profiles and 15–30 listings (items/services).

Given demo accounts, when used, then they are clearly labeled and safe (no real student data).

Given the demo, when rehearsed, then the seed data supports the planned narrative.

## E3 — Profiles (Student + Business)

### CM-US-015 — RLS policies for conversations and messages

As the platform, I want conversations and messages readable/writable only by participants so messaging stays private.

Priority: Must | Points: 5 | Owner: Backend Support | Sprint: S3

Dependencies: CM-US-013

Security/Data Notes: Participants table or conversation_members strategy must support policy checks; ensure performance with indexes.

Acceptance Criteria:

Given a conversation, when a participant selects messages, then they can read them; non-participants cannot.

Given sending a message, when inserted, then sender_id must equal auth.uid() (enforced by policy/constraint).

Given a user tries to access another conversation_id, when selecting, then RLS denies the query.

### CM-US-016 — Profile create/edit (baseline fields)

As a user, I want to create and edit my profile so that other students know who I am.

Priority: Must | Points: 5 | Owner: Frontend | Sprint: S3

Dependencies: CM-US-012, CM-US-014

Security/Data Notes: Profile writes must pass RLS; input validated with Zod; handle loading/error states.

Acceptance Criteria:

Given I am logged in, when I open Profile, then I can see my current profile or an onboarding prompt.

Given I edit name and bio, when I save, then changes persist and are visible on refresh.

Given validation rules, when fields are invalid, then save is blocked with clear messages.

### CM-US-017 — Business profile toggle + business fields

As a student offering services, I want to mark myself as a business and add business details so that buyers trust my offering.

Priority: Should | Points: 3 | Owner: Frontend + UX | Sprint: S3

Dependencies: CM-US-016

Security/Data Notes: No extra auth role; it’s a profile attribute; ensure fields aren’t abused (basic length limits).

Acceptance Criteria:

Given I toggle business mode, when enabled, then business name/category fields appear and are required.

Given I disable business mode, when saved, then business-only fields are hidden from my public profile.

Given other users view my profile, when business mode is enabled, then they see a clear badge indicating business account.

### CM-US-042 — Public profile view (read-only)

As a user, I want to view a seller’s profile so that I can trust who I’m contacting.

Priority: Must | Points: 3 | Owner: Frontend | Sprint: S4

Dependencies: CM-US-016, CM-US-014

Security/Data Notes: Profile reads allowed for authenticated users; RLS must not expose private fields if added later.

Acceptance Criteria:

Given I open a seller profile from a listing, when the page loads, then I see display name, bio, and business badge (if any).

Given the seller has no bio, when viewed, then the UI shows a sensible default/empty state.

Given I am not logged in, when I try to view profiles, then I am redirected to login (MVP is NJIT-only).

## E4 — Listing Data Model + Media

### CM-US-005 — Draft core data model (ERD + table list)

As a backend developer, I want an initial ERD and table list so that schema decisions are made early and don’t block implementation.

Priority: Must | Points: 5 | Owner: Backend Lead + Backend Support | Sprint: S1

Dependencies: None

Security/Data Notes: Include audit fields (created_at, updated_at) and soft delete columns.

Acceptance Criteria:

Given MVP requirements, when we draft the ERD, then it includes profiles, listings (items/services), listing_images, conversations, messages.

Given the ERD is done, when reviewed with frontend/UX, then required fields match the planned forms.

Given schema draft, when stored, then it is in docs/ (diagram + table definitions) and linked in the project board.

### CM-US-009 — Finalize schema requirements from wireframes

As a backend developer, I want final required fields for listings and profiles so that schema matches UI and avoids rework.

Priority: Must | Points: 3 | Owner: Backend Lead | Sprint: S2

Dependencies: CM-US-005, CM-US-006

Security/Data Notes: Fields designed to support RLS and soft delete.

Acceptance Criteria:

Given wireframes, when we extract fields, then we produce a data dictionary for profile fields and listing fields (item vs service).

Given data dictionary, when reviewed by team, then required vs optional fields are agreed.

Given agreement, when sprint ends, then schema decisions are documented and ready for migrations.

### CM-US-043 — Avatar upload (profile picture)

As a user, I want to upload an avatar so that my profile is recognizable.

Priority: Could | Points: 3 | Owner: Frontend + Backend Support | Sprint: S4

Dependencies: CM-US-016, CM-US-019

Security/Data Notes: Storage policy: only owner can write; consider signed URLs; restrict file types.

Acceptance Criteria:

Given I select an image under the size limit, when uploaded, then it saves to storage and updates my profile avatar URL.

Given invalid type/oversize, when uploaded, then I see a validation error and upload is blocked.

Given I replace my avatar, when saved, then the old avatar is not publicly accessible (or is replaced/cleaned up).

## E5 — Create & Manage Listings (Items + Services)

### CM-US-019 — Supabase Storage bucket for listing images

As a seller, I want to upload listing images so that my posts look legitimate and informative.

Priority: Must | Points: 5 | Owner: Backend Lead + Frontend | Sprint: S4

Dependencies: CM-US-013, CM-US-014

Security/Data Notes: Storage policies aligned with RLS; validate file type/size; avoid public access for drafts.

Acceptance Criteria:

Given a listing image upload, when I submit a valid image, then it is stored in the listing-images bucket under listing_id path.

Given a non-owner attempts to upload/delete images for my listing, when attempted, then storage policy denies it.

Given I view a listing, when images exist, then image URLs load correctly (signed or public per chosen rule).

### CM-US-020 — Create item listing (draft) from form

As a seller, I want to create an item listing so that I can sell a physical item to other NJIT students.

Priority: Must | Points: 5 | Owner: Frontend | Sprint: S4

Dependencies: CM-US-016, CM-US-019

Security/Data Notes: Server-side validation mirrored; owner_id set by backend/RLS; draft not visible to others.

Acceptance Criteria:

Given I’m logged in, when I open Post and choose Item, then I see item fields (title, description, price, quantity, condition).

Given I submit valid data, when saved, then a listing is created in draft status and appears in My Listings.

Given invalid data (e.g., negative price), when submitted, then the form shows validation errors and does not create the listing.

### CM-US-021 — Create service listing (draft) from form

As a student offering a service, I want to create a service listing so that others can hire me.

Priority: Must | Points: 5 | Owner: Frontend + UX | Sprint: S4

Dependencies: CM-US-017, CM-US-019

Security/Data Notes: Same listings table type=service; guard against spam with length limits and required fields.

Acceptance Criteria:

Given I select Service, when I open the form, then I see service fields (service type, rate, unit, availability notes).

Given I submit valid data, when saved, then it is created as a draft listing and appears in My Listings.

Given I’m not a business profile, when posting a service, then the app still allows it but encourages completing profile fields.

### CM-US-022 — Publish/unpublish listing

As a seller, I want to publish my listing when it’s ready so that others can see it.

Priority: Must | Points: 3 | Owner: Frontend + Backend Support | Sprint: S4

Dependencies: CM-US-020, CM-US-021

Security/Data Notes: RLS allows owner to update status; browse only selects published, non-deleted.

Acceptance Criteria:

Given a draft listing, when I click Publish, then status becomes published and it appears in Browse results.

Given a published listing, when I click Unpublish, then it disappears from Browse and remains in My Listings as draft.

Given required fields are missing, when I attempt to publish, then the app blocks publishing and shows what’s missing.

### CM-US-044 — My Listings dashboard

As a seller, I want a dashboard of my listings so that I can manage drafts and published posts.

Priority: Must | Points: 5 | Owner: Frontend | Sprint: S4

Dependencies: CM-US-020, CM-US-021

Security/Data Notes: Query uses auth.uid() and RLS; do not show other users’ listings.

Acceptance Criteria:

Given I open My Listings, when loaded, then I see my listings grouped by Draft and Published.

Given I click a listing, when selected, then I can navigate to edit or detail view.

Given I have no listings, when opened, then I see an empty state with a button to create one.

### CM-US-045 — Edit listing (item/service)

As a seller, I want to edit my listing so that I can update price, description, or availability.

Priority: Must | Points: 5 | Owner: Frontend + Backend Support | Sprint: S4

Dependencies: CM-US-022, CM-US-014

Security/Data Notes: RLS owner-only updates; validate input server-side too; keep audit updated_at.

Acceptance Criteria:

Given I own a listing, when I edit fields and save, then changes persist and reflect on Browse/Detail for published listings.

Given I do not own a listing, when attempting edit via URL, then access is denied.

Given invalid edits (e.g., empty title), when submitted, then validation blocks the save.

## E6 — Browse, Detail & Search

### CM-US-008 — Static page scaffold (routes + layout)

As a user, I want a clean navigation layout so that I can move between Browse, Post, Profile, and Messages.

Priority: Must | Points: 5 | Owner: Frontend | Sprint: S2

Dependencies: CM-US-001

Security/Data Notes: Guard routes later; for now no data access; ensure accessibility attributes.

Acceptance Criteria:

Given the app loads, when I navigate via navbar, then Browse/Post/Profile/Messages routes render.

Given mobile view, when I open the navbar, then it is responsive and accessible.

Given placeholder pages, when sprint ends, then each page has an empty state and a clear call-to-action.

### CM-US-023 — Browse feed (published listings only) + pagination

As a user, I want to browse published listings so that I can discover what’s available.

Priority: Must | Points: 5 | Owner: Frontend | Sprint: S4

Dependencies: CM-US-022

Security/Data Notes: Use TanStack Query; only published listings returned; handle loading/error states.

Acceptance Criteria:

Given published listings exist, when I open Browse, then I see a list/grid of cards with image, title, price/rate, and type.

Given I scroll, when I reach the end, then more results load (pagination/infinite scroll).

Given there are no listings, when I open Browse, then I see a clear empty state and a button to Post.

### CM-US-024 — Listing detail page

As a user, I want to view listing details so that I can decide to contact the seller.

Priority: Must | Points: 3 | Owner: Frontend | Sprint: S4

Dependencies: CM-US-023

Security/Data Notes: Enforce visibility rules; RLS and server filtering must prevent non-owners from reading drafts.

Acceptance Criteria:

Given I click a listing card, when detail page loads, then I see images, description, price/rate, and seller profile link.

Given I own the listing, when viewing detail page, then I see Edit and Unpublish/Delete actions.

Given the listing is unpublished/deleted, when a non-owner tries to access it via URL, then access is blocked or shows not found.

### CM-US-025 — Simple search (keyword + type filter)

As a user, I want to search listings so that I can find items or services quickly.

Priority: Should | Points: 3 | Owner: Frontend + Backend Support | Sprint: S4

Dependencies: CM-US-023

Security/Data Notes: Use safe parameterized queries; consider indexes on title/description; avoid advanced filters per scope.

Acceptance Criteria:

Given I enter a keyword, when searching, then results match title/description (case-insensitive).

Given I toggle Item/Service, when filter applied, then results are restricted to that type.

Given I clear the search, when cleared, then I return to the default browse feed.

### CM-US-046 — Soft delete listing

As a seller, I want to remove my listing so that it no longer appears in the marketplace.

Priority: Must | Points: 3 | Owner: Backend Support + Frontend | Sprint: S4

Dependencies: CM-US-014

Security/Data Notes: Soft delete standard per checklist; browse selects non-deleted; consider cascade for images/messages.

Acceptance Criteria:

Given I own a listing, when I delete it, then it is soft-deleted (deleted_at set) and removed from Browse results.

Given I deleted a listing, when I view My Listings, then it appears under Removed (optional) or is hidden.

Given another user has a saved URL, when they visit it, then they see Not Found or Listing Unavailable.

## E7 — Messaging (Conversations + Messages)

### CM-US-027 — Create or get conversation from listing

As a buyer, I want to start a conversation from a listing so that I can coordinate with the seller.

Priority: Must | Points: 5 | Owner: Backend Support + Frontend | Sprint: S5

Dependencies: CM-US-024, CM-US-015

Security/Data Notes: RLS participants-only; prevent duplicates with unique constraint; store listing_id on conversation.

Acceptance Criteria:

Given I view a listing not owned by me, when I click Message, then a conversation is created or reused for that listing + seller.

Given the conversation exists, when I open Messages, then it appears in my inbox.

Given I try to message myself, when attempted, then the action is blocked.

### CM-US-028 — Inbox view (list conversations with previews)

As a user, I want an inbox so that I can find active conversations quickly.

Priority: Must | Points: 5 | Owner: Frontend | Sprint: S5

Dependencies: CM-US-027

Security/Data Notes: Only load conversations the user participates in; avoid N+1 queries; consider a view or join query.

Acceptance Criteria:

Given I have conversations, when I open Messages, then I see a list sorted by latest message time.

Given a conversation, when I view the list, then I see listing title (if present) and last message preview.

Given I have no conversations, when I open Messages, then I see an empty state with guidance.

### CM-US-029 — Message thread + send message

As a user, I want to read and send messages so that I can coordinate the handoff for an item/service.

Priority: Must | Points: 8 | Owner: Frontend + Backend Support | Sprint: S5

Dependencies: CM-US-027

Security/Data Notes: Sender_id must match auth.uid(); validate content length; store created_at; RLS enforces read/write.

Acceptance Criteria:

Given I open a conversation, when messages load, then I see them in chronological order with sender and timestamp.

Given I type a message and send, when submitted, then it appears immediately in the thread and persists after refresh.

Given message send fails, when failure occurs, then I see a clear error and can retry.

### CM-US-030 — Realtime updates (or polling fallback) for messages

As a user, I want near real-time messaging so that conversations feel responsive.

Priority: Should | Points: 5 | Owner: Frontend | Sprint: S5

Dependencies: CM-US-029

Security/Data Notes: Use Supabase Realtime if feasible; ensure filters by conversation_id; handle disconnects.

Acceptance Criteria:

Given I am viewing a conversation, when the other participant sends a message, then it appears without a full page refresh.

Given realtime is unavailable, when subscription fails, then the app falls back to polling every few seconds.

Given I leave the page, when unmounted, then subscriptions/polling are stopped to avoid leaks.

### CM-US-049 — Performance baseline: indexes + query limits

As a user, I want pages to load quickly so that browsing feels smooth.

Priority: Should | Points: 3 | Owner: Backend Lead | Sprint: S5

Dependencies: CM-US-013, CM-US-023

Security/Data Notes: Indexing and safe query patterns; RLS can impact query plans—test in staging.

Acceptance Criteria:

Given browse/search queries, when executed, then they use indexes on status/type/created_at and avoid full-table scans where possible.

Given pagination, when fetching, then queries use limit/offset or cursor patterns and do not load all rows.

Given an error in query, when it happens, then app fails gracefully with retry.

## E8 — Booking Lite (Optional, built on messaging)

### CM-US-047 — Messaging schema + RLS validation smoke checks

As a backend developer, I want messaging tables and RLS verified with basic queries so that frontend can build safely.

Priority: Must | Points: 5 | Owner: Backend Support | Sprint: S4

Dependencies: CM-US-013, CM-US-015

Security/Data Notes: RLS + constraints verified; document policy in docs.

Acceptance Criteria:

Given migrations, when applied, then conversations/messages (and members if used) tables exist with constraints.

Given two test users, when querying messages, then only participants can read and insert messages.

Given a spoofed sender_id, when inserted, then it is rejected by policy/constraint.

## E9 — DevOps, Repo Standards & CI/CD

### CM-US-001 — Monorepo initialization + conventions

As a developer, I want a consistent repo structure and conventions so that the team can work in parallel without chaos.

Priority: Must | Points: 3 | Owner: Backend Support + Frontend | Sprint: S1

Dependencies: None

Security/Data Notes: Repo structure per proposal; no secrets committed; .env.example present.

Acceptance Criteria:

Given a new clone, when I run the standard setup steps, then the web app starts locally without manual fixes.

Given a PR is opened, when branch/commit conventions are violated, then the team has a documented standard to follow (docs + templates).

Given the repo is created, when we browse folders, then apps/web, supabase/, docs/, and .github/ exist and match the agreed layout.

### CM-US-002 — CI pipeline baseline (lint/type/build)

As a developer, I want CI checks on every PR so that broken code doesn’t get merged.

Priority: Must | Points: 3 | Owner: Backend Support | Sprint: S1

Dependencies: CM-US-001

Security/Data Notes: GitHub Actions; no secrets in CI logs; checks run on PR.

Acceptance Criteria:

Given a PR is opened, when CI runs, then lint + typecheck + build complete successfully or block the merge.

Given CI fails, when I view logs, then the failure reason is clear and actionable.

Given a PR includes changes, when checks pass, then a green status is shown before merge.

### CM-US-018 — Environment variables + secrets strategy

As a developer, I want a clear environment variable setup so that local dev and deploy are consistent and secure.

Priority: Must | Points: 2 | Owner: Backend Support + PM | Sprint: S3

Dependencies: CM-US-001

Security/Data Notes: Document VITE_SUPABASE_URL and VITE_SUPABASE_ANON_KEY; restrict access to secret keys.

Acceptance Criteria:

Given repo docs, when I follow setup steps, then I can create a .env.local from .env.example.

Given secrets, when stored, then only public Supabase anon keys are used in frontend; service role keys are never committed.

Given deploy, when CI runs, then environment variables are loaded via Vercel/CI secrets.

### CM-US-031 — Booking request message type (optional)

As a buyer, I want to send a booking request so that a seller can accept/decline a proposed time for a service.

Priority: Could | Points: 5 | Owner: Frontend + Backend Support + UX | Sprint: S5

Dependencies: CM-US-029

Security/Data Notes: Store booking fields on message or separate booking table; RLS ensures only seller can change status.

Acceptance Criteria:

Given a service listing, when I click Request Booking, then I can propose a date/time and add a note.

Given a booking request is sent, when seller views thread, then booking status shows as Pending.

Given seller responds, when accepted/declined, then status updates and buyer sees the new status.

### CM-US-032 — Production deployment (Vercel + Supabase) with environments

As a team, we want a working deployment so that we can demo from a stable URL.

Priority: Must | Points: 5 | Owner: Backend Lead + Frontend | Sprint: S5

Dependencies: CM-US-002, CM-US-029

Security/Data Notes: No service role keys in frontend; RLS active in production; verify email confirmation flow works.

Acceptance Criteria:

Given staging/production config, when we deploy, then the app runs on Vercel with correct Supabase URL/keys.

Given a new release, when deployed, then rollback steps are documented and tested.

Given production is live, when a user signs up (test account), then core flows work end-to-end.

### CM-US-037 — Project board workflow (columns + labels + templates)

As a team, we want a consistent project board workflow so that work is tracked and ownership is clear.

Priority: Must | Points: 2 | Owner: PM | Sprint: S2

Dependencies: None

Security/Data Notes: No security notes; process story.

Acceptance Criteria:

Given the board, when set up, then it has columns matching sprint flow (Backlog, Ready, In Progress, Review, Done).

Given issues/stories, when created, then they use a common template including AC, points, owner, and sprint label.

Given sprint planning, when a sprint starts, then selected stories are assigned and scoped to capacity.

### CM-US-038 — API contract + data dictionary doc

As a developer, I want an agreed API contract and data dictionary so that frontend and backend build to the same spec.

Priority: Must | Points: 3 | Owner: Backend Lead + Frontend | Sprint: S2

Dependencies: CM-US-005, CM-US-009

Security/Data Notes: Include RLS assumptions in docs; avoid exposing secret keys.

Acceptance Criteria:

Given core flows, when contract is written, then it includes endpoints/queries for auth, profiles, listings, messages.

Given contract changes, when updated, then versioning notes are recorded and stakeholders notified.

Given the docs, when a dev joins, then they can understand request/response shapes without reading code.

### CM-US-039 — Supabase client wrapper + service layer scaffold

As a frontend developer, I want a single Supabase client wrapper and service modules so that pages never call Supabase directly.

Priority: Must | Points: 5 | Owner: Frontend | Sprint: S3

Dependencies: CM-US-001, CM-US-011

Security/Data Notes: Never expose service role keys; wrapper uses anon key; follow proposal rule: UI never calls Supabase directly.

Acceptance Criteria:

Given the codebase, when calling data, then pages/components use feature services (e.g., listings.service.ts).

Given the wrapper, when session changes, then auth state is centralized and reusable across the app.

Given a new feature, when added, then it follows the layer boundaries documented in the proposal.

## E10 — Testing, QA & Demo Scripts

### CM-US-003 — Definition of Done + PR checklist

As a PM, I want a Definition of Done and PR checklist so that every increment is demo-ready and testable.

Priority: Must | Points: 2 | Owner: PM | Sprint: S1

Dependencies: CM-US-001

Security/Data Notes: DoD includes RLS considerations for any data access change.

Acceptance Criteria:

Given a story is moved to Done, when we verify the DoD checklist, then acceptance criteria are met and basic error handling exists.

Given a PR is submitted, when reviewer checks the PR template, then tests/lint/build and screenshots (if UI) are included.

Given new endpoints/contracts, when merged, then docs are updated (API contract or README).

### CM-US-004 — User research plan + survey draft

As a PM, I want a lightweight research plan and survey so that we validate the MVP flows with real NJIT students early.

Priority: Must | Points: 3 | Owner: PM + UX | Sprint: S1

Dependencies: None

Security/Data Notes: No PII stored in repo; responses stored in shared doc drive.

Acceptance Criteria:

Given a draft survey, when reviewed by the team, then it covers buying, selling, services, and trust concerns.

Given we run the survey, when sprint ends, then we have a target list of at least 10 participants and a plan to recruit them.

Given results arrive, when summarized, then top 5 insights are documented with recommended UX changes.

### CM-US-006 — Low-fidelity wireframes for core flows

As a user, I want to see simple wireframes so that I understand how the app will work before development.

Priority: Must | Points: 3 | Owner: UX | Sprint: S2

Dependencies: CM-US-004

Security/Data Notes: No security notes; but include trust messaging (NJIT-only).

Acceptance Criteria:

Given core flows, when wireframes are created, then they cover auth, browse, listing detail, post listing, profile, messages.

Given a review session, when we walkthrough wireframes, then feedback is captured and prioritized.

Given wireframes are approved, when sprint ends, then they are shared in Figma and linked from the project board.

### CM-US-007 — Branding + design tokens v1

As a developer, I want basic design tokens so that the UI is consistent and fast to implement.

Priority: Should | Points: 3 | Owner: UX + Frontend | Sprint: S2

Dependencies: CM-US-006

Security/Data Notes: Avoid exposing sensitive info; consider accessible contrast ratios.

Acceptance Criteria:

Given branding assets, when delivered, then logo, color palette, and typography are documented.

Given tokens, when implemented, then primary/secondary colors and type scale are available in Tailwind config or CSS variables.

Given components, when built, then they reuse tokens and avoid one-off styling.

### CM-US-026 — Midterm demo script + walkthrough deck (lightweight)

As a team, we want a midterm demo script so that we can present a coherent end-to-end MVP slice.

Priority: Must | Points: 3 | Owner: PM | Sprint: S4

Dependencies: CM-US-023, CM-US-024

Security/Data Notes: Avoid promising payments/reviews; highlight NJIT-only trust and Supabase security.

Acceptance Criteria:

Given completed features, when we rehearse, then demo covers auth → profile → post listing → browse → view listing.

Given the deck, when reviewed, then it matches current product and includes risks/next steps.

Given submission requirements, when we submit, then midterm deliverables are complete by Apr 3.

### CM-US-033 — E2E smoke tests for core flows

As a team, we want automated smoke tests so that we catch obvious breakage before demos.

Priority: Should | Points: 5 | Owner: Backend Support + Frontend | Sprint: S5

Dependencies: CM-US-032

Security/Data Notes: Use Playwright as suggested; ensure test accounts and cleanup; don’t expose secrets in logs.

Acceptance Criteria:

Given CI runs, when smoke tests execute, then sign in → create listing → browse → open detail passes on staging.

Given messaging is enabled, when test runs, then create conversation and send a message passes.

Given tests fail, when failure occurs, then logs/screenshots are captured for debugging.

### CM-US-034 — Final usability test + polish backlog

As a UX/UI designer, I want a final usability pass so that the UI is clean and demo-ready.

Priority: Must | Points: 3 | Owner: UX + Frontend + PM | Sprint: S5

Dependencies: CM-US-032

Security/Data Notes: Avoid scope creep; prioritize blockers to demo; keep accessibility in mind.

Acceptance Criteria:

Given MVP is integrated, when we test with 5+ students, then top issues are captured with severity labels.

Given critical issues, when fixed, then we verify improvements with at least one re-test.

Given UI polish changes, when merged, then they do not break core flows and meet DoD.

### CM-US-035 — Final presentation narrative + paper outline

As a PM, I want a coherent final narrative so that the team can present and write the final paper efficiently.

Priority: Must | Points: 3 | Owner: PM | Sprint: S5

Dependencies: CM-US-032

Security/Data Notes: Do not claim out-of-scope features; emphasize Supabase RLS and NJIT-only trust.

Acceptance Criteria:

Given the project state, when we draft the deck, then it includes problem, solution, demo, architecture, and future scope (payments/reviews).

Given deadlines, when we prepare, then final presentation is ready by May 3 and paper outline by May 7.

Given the deck, when rehearsed, then every team member has a speaking role and a backup plan for demo failures.

### CM-US-036 — Marketplace rules & restricted content policy (MVP)

As a PM, I want clear marketplace rules (allowed items/services) so that the app stays safe and within school expectations.

Priority: Should | Points: 2 | Owner: PM | Sprint: S2

Dependencies: CM-US-004

Security/Data Notes: Policy only; no automated moderation in MVP; store in docs and link in UI.

Acceptance Criteria:

Given the MVP scope, when rules are written, then they define prohibited items/services and basic enforcement approach (manual for MVP).

Given the rules, when users view Post, then they can access the rules link before posting.

Given a report from user research, when risks are found, then rules are updated and shared with the team.

### CM-US-040 — Error handling patterns (loading, empty, failure states)

As a user, I want clear loading and error states so that the app feels reliable.

Priority: Must | Points: 3 | Owner: Frontend + UX | Sprint: S3

Dependencies: CM-US-008

Security/Data Notes: Avoid leaking raw errors; map Supabase errors to safe messages.

Acceptance Criteria:

Given a data request, when loading, then a skeleton/spinner shows and buttons are disabled appropriately.

Given a network error, when it happens, then user sees a friendly message and a Retry action.

Given no data, when empty, then a helpful empty state is displayed (not a blank page).

### CM-US-048 — Account deactivation (soft delete) UX

As a user, I want to deactivate my account so that I can leave the platform without exposing my data.

Priority: Could | Points: 5 | Owner: Backend Lead + Frontend | Sprint: S5

Dependencies: CM-US-032, CM-US-014

Security/Data Notes: Prefer soft delete; ensure RLS prevents access; handle orphaned listings/messages carefully.

Acceptance Criteria:

Given I am logged in, when I request deactivation, then I must confirm and understand consequences.

Given my account is deactivated, when I try to log in, then access is blocked and I see a support message.

Given my account is deactivated, when others view my listings/profile, then they are hidden or show unavailable.